## JS Features (hidden)
| Client: Childhoodtrust Design & Development Total Estimated Days | WORK BREAKDOWN STRUCTURE
Task No. | Task | Service Provider | Dependency | Task Status | Frontend Days | Fullstack Days | AI Development | PM / Strategy Days | Design Days | QA Days | Cost | Start Date | Finish Date | Estimated Duration | Month Number | Notes / Questions / Assumptions
0
Foundation & Core Setup
| CMS Setup & Configuration |  |  |  |  | 18
| Custom Theme Development |  |  |  | 48
| Content Migration |  |  |  |  | 30
| User Management System |  |  |  |  | 48
| SEO & Performance |  |  |  |  | 18
| Basic Forms & Contact |  |  |  | 18
| Website Testing & Launch | [8 empty] | 16
| Authentication & SSO |  |  |  |  | 32
| Basic Chat System |  |  |  |  | 24
| Real-time Infrastructure |  |  |  |  | 24
| AI Content Moderation | [5 empty] | 24
| Video Meeting Integration |  |  |  |  | 24
| Admin Dashboard |  |  |  | 48
| Mobile Chat Optimization |  |  |  | 30
| Hub Testing & Integration | [8 empty] | 24
| Directory Database Design |  |  |  |  | 30
| Advanced Search & Filtering |  |  |  |  | 48
| Charity Profile Management |  |  |  |  | 48
| Directory User Interface |  |  |  | 30
| Bulk Data Import Tools |  |  |  |  | 18
| Directory Testing & Polish | [8 empty] | 18
| Networking Platform Core |  |  |  |  | 78
| Marketplace Features |  |  |  |  | 78
| Document Management System |  |  |  |  | 48
| Advanced AI Tools | [5 empty] | 48
| Analytics & Reporting |  |  |  |  | 48
API Development
| API Development |  |  |  |  | 48
Advanced Features & Add-ons
| Accessibility Enhancement |  |  |  | 48
| Content Management Workflows |  |  |  |  | 48
| Advanced Chat Features |  |  |  |  | 48
| Email Integration |  |  |  |  | 30
| Backup & Disaster Recovery |  |  |  |  | 30
Project Management
| Project Management | [6 empty] | 78
Launch Support / Maintenance
| User Acceptance Testing | [8 empty] | 30
| Launch Coordination |  |  |  |  | 48 |  | 30
Post-Launch Support
Total Estimated Days |  |  |  |  | 222 | 866 | 72 | 108 | 0 | 88 | [5 empty] | ~

## Features
| Client: Fab4050 App Development Total Estimated Days |  |  | WORK BREAKDOWN STRUCTURE
Task No. | Task | Phase |  | Assigned Technology | Dependency | Task Status | Frontend Hours | Backend Hours | AI Hours | PM Hours | Design Hours | QA Hours | Cost | Start Date | Finish Date | Estimated Duration | Month Number | Notes / Questions / Assumptions
0 | Project Management
| Project Management | [8 empty] | 42
1 | Feature Breakdown
1.1 | Develop secure user registration and login system | Firebase Authentication | 24 | Firebase Authentication |  |  |  | 24
1.2 | Implement profile creation and personalization | React Native | 24 | React Native |  |  | 24
1.3 | Integrate personalized workout plans with video demonstrations | React Native | 40 | React Native |  |  | 40
1.4 | Develop a nutrition guidance and meal plan feature | React Native | 32 | React Native |  |  | 32
1.5 | Create meditation and affirmation content player | React Native | 20 | React Native |  |  | 20
1.6 | Build interactive community forums with messaging capabilities | React Native | 60 | React Native |  |  | 60
1.7 | Develop scheduling system for weekly virtual community calls | Node.js | 40 | Node.js |  |  |  | 40
1.8 | Integrate AI chatbot for menopause-related queries | Python, Google Gemini | 120 | Python, Google Gemini |  |  |  | 120
1.9 | Create symptom tracking interface for user input | React Native | 24 | React Native |  |  | 24
1.1 | Implement in-app purchase mechanisms | Stripe | 32 | Stripe |  |  |  | 32
1.11 | Build subscription management system | Firebase Functions | 64 | Firebase Functions |  |  |  | 64
1.12 | Develop content management system for expert content updates | Node.js | 90 | Node.js |  |  |  | 90
1.13 | Create an analytics dashboard for user engagement tracking | D3.js, Node.js | 40 | D3.js, Node.js |  |  | 40
1.14 | Ensure GDPR compliance and data privacy measures | AWS, Custom Middleware | 40 | AWS, Custom Middleware |  |  |  | 40
1.15 | Implement scalable architecture for future expansion | Kubernetes | 60 | Kubernetes |  |  |  | 60
1.16 | Design a user-friendly interface with accessibility in mind | React Native | 32 | React Native |  |  | 32
1.17 | Conduct user onboarding and privacy consent flows | React Native | 20 | React Native |  |  | 20
1.18 | Integrate AI/LLM for enhanced chatbot functionalities | Hugging Face | 100 | Hugging Face |  |  |  | 100
1.19 | Develop curated dashboards for data insights | Tableau | 40 | Tableau |  |  |  | 40
1.2 | Generate trend reports and predictive analytics models | Python, Pandas | 60 | Python, Pandas |  |  |  | 60
2 | Post-Launch Support
| - Bug fixes | Support & Analytics
| - User support | Support & Analytics
| - Performance monitoring | Support & Analytics
Total Estimated Days | [6 empty] | 84 | 84 | 0 | 42 | 40 | 0 | [5 empty] | ~

## Estimates-old (hidden)
Team
Phase 2
Role | Day Rate (Ex Vat) | Investment | Mar '25 | Aug '24 | Notes
Senior Solutions Architect | 600 | 0 | 0 | 0
Senior Frontend Engineer | 600 | 50400
Full Stack Engineer | 600 | 50400
Project Manager | 660 | 27720
Product Designer | 660 | 26400
AI Engineer | 660 | 0
QA | 660 | 0
Senior Brand Designer | 600 | 0 | 0 | 0
Blott Discount* |  | 0
Total (Ex VAT) |  | 154920 | 0 | 0
Total (Inc VAT) |  | 185904 | 0 | 0
Total Investment (Ex VAT) | 154920
Discounted Total Investment (Ex VAT) | £12,000.00

## Estimates (hidden)
Team
Phase 2
Role | Hourly Rate (Ex Vat) | Investment | Mar '25 | Aug '24 | Notes
Senior Solutions Architect | 600 | 0 | 0 | 0
Senior Frontend Engineer | 75 | 6300
Full Stack Engineer | 75 | 6300
Project Manager | 82.5 | 3465
Product Designer | 82.5 | 3300
AI Engineer | 82.5 | 0
QA | 82.5 | 0
Senior Brand Designer | 600 | 0 | 0 | 0
Blott Discount* |  | 0
Total (Ex VAT) |  | 19365 | 0 | 0
Total (Inc VAT) |  | 23238 | 0 | 0
Total Investment (Ex VAT) | 19365
Discounted Total Investment (Ex VAT) | £12,000.00

## Investment Assets
Team
Phase 2
Role |  | Investment | Mar '25 | Aug '24 | Notes
Backend Engineering | 540 | 45360 | 0 | 0
Frontend Engineering | 540 | 45360
Product Design (UI/UX) | 540 | 21600
Product Manager | 540 | 22680
Support & Analytics | 540
Blott Discount* |  | 0
Total (Ex VAT) |  | 135000 | 0 | 0
Total (Inc VAT) |  | 162000 | 0 | 0
Total Investment (Ex VAT) | 135000
Discounted Total Investment (Ex VAT) | £12,000.00

## Maxmedias Information (hidden)
Supporting Documentation | Links